## Road Map
Ez Cars
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 10/29/2024 | SPRINT2 - 11/19/2024 | SPRINT3 - 12/17/2024
01. Profile Management | 01.01 Create Account | 3 | X
| 01.02 Modify Account | 3 | X
| 01.03 View Account Summary | 4 | X
| 01.04 Access Customer Support | 2 | X
02. Vehicle Search | 02.01 Search Vehicles | 2 | X
| 02.02 Compare Vehicles | 4 |  | X
02.03 Filter Vehicles
| 02.04 View Vehicle Information | 2 | X
03. Booking Management | 03.01 Book Vehicles | 4 |  | X
| 03.02 Send Booking Reminder | 4 |  | X
| 03.03 Manage Bookings | 3 |  |  | X
| 03.04 View Bookings | 4 |  | X
04. Payments and Ratings | 04.01 Process Payments | 4 |  |  | X
| 04.02 View Payment History | 2 |  |  | X
| 04.03 Post Rating/Review | 4 |  |  | X
| 04.04 View Ratings | 2 |  |  | X
05. Promotions | 05.01 Create Deal/Event Post
05.02 View Post History and Statistical Data
05.03 Send Promotional Notifications
|  | VELOCITY: | 16 | 16 | 15

## Jira Road Map
Timeline/Roadmap View: Months
Timeline/Roadmap View: Weeks